## Slide 1: Best Practices to Engage Stakeholders to Effectively Negotiate Construction Contracts
Presented by:
Richard F. King, CPA, CCIFP
Schlouch incorporated
Ronald L. Williams, Partner
Fox Rothschild llp
Wendy Byerly, Director, Contract Controls
Allan Myers

## Slide 2: Agenda
Mindset & Approach to Contract Review
Involving Internal & External Subject Matter Experts / Stakeholders
Negotiating with Outside Parties –Balancing Risk & Relationships
Assessing your Project & Contract Risks / Key Focus Areas
Working with Your Attorney for Positive Outcomes While Managing Costs
Role Play / Negotiation Scenarios

## Slide 3: Poll #1
Do you review contracts which your company is going to sign?
Always
Sometimes
Occasionally
Never

## Slide 4: Poll #1 – Things to Consider
Construction Contracts Aren’t the Only Documents CFP’s Can Negotiate:
  Software License Agreements
  Engagement Letters w/ Accountants, Attorneys & Outside Advisors
  Administrative Services Agreements with Providers
  Equipment Purchase / Rental & Lease Contracts
  & More
They All Should Be Read & Negotiated

## Slide 5: Poll #2
How Do You Feel About Negotiating Contracts?
Can’t Wait to Crush the Opposition
I Just Sign It – You Can’t Negotiate with a Customer
I’ll Do the Best I Can to Negotiate & Manage Our Risk
I’d Rather Have a Root Canal than Negotiate

## Slide 6: Mindset / Approach
Notes: Dr. Chester Karrass

## Slide 7: Mindset / Approach

## Slide 8: Mindset / Approach
Contract Negotiation is Risk Management & a Key Contributor to Your P&L
Contract Negotiation is Relationship Management
Contract Negotiation is a “Team Sport”
Notes: Example of tapping counsel in if other side is not taking reasonable approach – R/E & Dev counsel on construction doc’s

## Slide 9: Mindset / Approach
Is Contract Negotiation a “Planned Conflict”?
Are we in disagreement or are we trying to build consensus?
        OR
Is Contract Negotiation a “Crucial Conversation”?
  Crucial – “decisive or critical, especially in the success or failure of something”
  Conversation – “the informal exchange of ideas by spoken words”

## Slide 10: Consider / Assess Your Starting Point
Who are you negotiating with?
What is our relationship / experience with this party?
Who has the best relationship & how are they involved with this project?
Who are the Stakeholders?
What is the size and risks on the project?
What is the current economic market / environment?
Quick Assessment (1-10) on Starting Point  1 = Completely in Our Favor & 10 = Completely
in Their Favor

## Slide 11: Key Areas & Relevant Stakeholders
Plans & Specifications – Estimator
Scope – Estimator, Superintendent / Project Manager, Subject Matter Experts for technical work
Schedule – Estimator, Superintendent / Project Manager
Indemnification & Insurance – Insurance Agent & Attorney
Legal Terms & Conditions - Attorney

## Slide 12: Communication
Who
When
How
Establish relationship & build trust / confidence with an eye towards having a fair contract and excellent project.

## Slide 13: Key Areas to Review
Contract Documents
Scope
Subsurface Conditions or Unknown Conditions
Payment & Evidence of Funding
Change Orders
Schedule / No Damages for Delay / LD’s
Bonds & Bond Forms
Indemnification
Insurance
Warranties / Project Close Out
Dispute Resolution

## Slide 14: Contract Documents
Review Full List of Documents
Drawing List
Owner Contract
Precedence of Documents

## Slide 15: Scope
Incorporation of bid proposals, qualifications and exclusions
Comparison of bid documents vs. contract documents, drawings list, etc.
Standard of Performance – Contract Documents vs. Intent
Notes: Obligation > Contract Documents, Bid Proposal and Qualifications & Exclusions

## Slide 16: Sample Scope Provision
“Subcontractor assumes toward Contractor all of the obligations of Contractor under the Contract Documents…The Subcontractor’s Work, whether or not shown on the drawings, mentioned in the Specifications or described in any Contract Documents, and any amendments shall be performed by Subcontractor as part of this Subcontract. The Subcontractor ensures that its Work will result in a fully functioning system.”
Notes: Obligation > Contract Documents, Bid Proposal and Qualifications & Exclusions

## Slide 17: Revised Scope Provision
“Subcontractor assumes toward Contractor all of the obligations of Contractor under the Contract Documents…The Subcontractor’s Work, whether or not shown on the drawings, mentioned in the Specifications or described in any Contract Documents, and any amendments shall be performed by Subcontractor as part of this Subcontract. The Subcontractor ensures that its Work will result in a fully functioning system. Notwithstanding the forgoing, the Work shall not include items which are specifically excluded or clarified in Subcontractor’s Proposal, Attachment A. Subcontractor shall have the same benefit…”
Notes: Obligation > Contract Documents, Bid Proposal and Qualifications & Exclusions

## Slide 18: Subsurface Conditions or Unknown Conditions
Site Condition Review
Ability to rely on expert reports
Unclassified
Hazardous Substances
Utility Conflicts

## Slide 19: Sample Subsurface Clause
“Contractor acknowledges that the subsurface conditions have been provided for in the Contract Sum and shall not be considered a Change Order an item in which a Change Order which results in an increase to the Contract Sum shall be permitted.”

## Slide 20: Revised Subsurface Clause
“Contractor acknowledges that the subsurface conditions, excluding hazardous materials, sinkholes, frost excavation and measures to remedy excessive moisture to meet design requirements, have been provided for in the Contract Sum and shall not be considered a Change Order an item in which a Change Order which results in an increase to the Contract Sum shall be permitted. To the extent the Contractor discovers subsurface conditions that are excluded herein, the Owner and Contractor shall agree on a Change Order.”

## Slide 21: Payment Terms & Evidence of Funding
Pay If Paid, Condition Precedent
Retainage Terms
Reduction of Retainage
Definitions of Substantial and Final Completion
Administrative Process / Documentation with Progress Billings
Lien Releases
Remedies for Non-Payment

## Slide 22: Sample Payment Terms & Evidence of Funding Clause
“An amount equal to ninety percent (90%) of the amount approved by Contractor shall be paid within thirty (30) days of requisition or within ten (10) days of receipt of payment from Owner, whichever is later. The obligation of Contractor to make payments to Subcontractor hereunder is subject to the condition precedent that Contractor has been paid by Owner.”

## Slide 23: Revised Payment Terms & Evidence of Funding Clause
“An amount equal to ninety percent (90%) of the amount approved by Contractor shall be paid within thirty (30) days of requisition or within ten (10) days of receipt of payment from Owner, whichever is later and in all cases within sixty (60) days of invoice date unless payments are otherwise withheld per the terms of this Agreement.”

## Slide 24: Sample Retainage Release Clause
“Final payment shall be made within thirty (30) days after Final Completion of the Project and acceptance by the Owner or within ten (10) days after receipt of final payment from Owner, whichever is later. The obligation for Contractor to make final payment is subject to the following conditions:…”

## Slide 25: Revised Retainage Release Clause
“Retainage shall be reduced to five percent (5%) when the Work is fifty percent (50%) complete. Retainage shall be further reduced to 150% the value of the punch list upon Substantial Completion of the Work. Final payment shall be made within thirty (30) days after Final Completion of the Work and acceptance by the Owner or within ten (10) days after receipt of final payment from Owner, whichever is later. The obligation for Contractor to make final payment is subject to the following conditions:… <<limit conditions>>”

## Slide 26: Change Orders
Proper Notice & Time to Prepare
Advance Waivers
Adjustment in Cost & Time, if applicable
Conditional Upon Payment from Owner
Change Directives Permitted
Open Cap on Unapproved CO’s
Pricing Methods & Documentation

## Slide 27: Schedule / No Damages for Delay/ LD’s
“Moving Target” Schedule
Milestone Dates are Adjustable
Permissible Delays
Conditioned Upon Owner Approval
No Damages for Delay
Liquidated Damages / Proportional / Caps
Opportunity to Cure
Changes, Acceleration, Out-of-Sequence
No Waiver of Consequential Damages

## Slide 28: Bonds & Bond Forms
Bid Bonds to Private Customers – condition bond obligation on funding and mutually agreed contract
Payment Bond Forms
Maintenance Bond Terms & Length

## Slide 29: Indemnification
Limited Form
Scope - Limit to Bodily Injury & Property Damage
Not for Another Party’s Sole Negligence
Indemnified Parties
Defense Obligations
Indemnification for claims by your employee’s

## Slide 30: Sample Indemnification Clause
“To the fullest permitted by law, Subcontractor shall defend, indemnify and hold harmless, the Contractor (including affiliates, subsidiaries, their consultants, agents and employees), the Owner, the Architect, agents and employees of any of them from and against all claims, causes of action, demands, damages, fines, penalties, losses… and expenses, including but not limited to attorney’s fees, resulting from, alleged to arise, incidental to from or in any way connected with Subcontractor’s performance…”

## Slide 31: Revised Indemnification Clause
“To the fullest permitted by law, Subcontractor shall defend, indemnify and hold harmless, the Contractor (including affiliates, subsidiaries, their consultants, agents and employees), the Owner, the Architect, agents and employees of any of them from and against all claims, causes of action, demands, damages, fines, penalties, losses… and expenses, including but not limited to attorney’s fees, resulting from, alleged to arise, incidental to from or in any way connected with Subcontractor’s performance…”

## Slide 32: Insurance
Primary and Non-contributory
Endorsements (Nothing before 7/04)
Waiver of Subrogation
Limits
Completed Operations
Limits Applicable to Subs
Gap in Contract vs. Insurance Coverage

## Slide 33: Warranties / Project Close Out
Time of Commencement
Term
Exclusions
Project Close Out Requirements & Documentation

## Slide 34: Sample Warranty / Project Close Out Clause
“ Subcontractor shall warrant its Work against all defects…for the greatest extent and duration called for in the Contract Documents, but in no event less than one (1) year from Final Completion of the entire Project.”

## Slide 35: Revised Warranty / Project Close Out Clause
“ Subcontractor shall warrant its Work against all defects…for the greatest extent and duration called for in the Contract Documents, but in no event more than one (1) year from Final Completion of the Work.”

## Slide 36: Dispute Resolution
Method – Pick One
Venue
Governing Law
Understanding how/when/what of Claim preservation

## Slide 37: Effective Use of Legal Counsel
Ron to add notes

## Slide 38: Third Party Considerations & Issues
Contractor’s Consent & Assignment
Consultants
Inspecting Parties
Developer’s Agreement
Other Parties’ Obligations

## Slide 39: Role Play / Negotiation Scenario
WENDY & RICH DISCUSSED ELIMINATING THIS SLIDE AND EXERCISE.
Retainage vs. Indemnification – provide sample provisions
Owner
  Only Paid when Approved by Lender, numerous parties
  Retainage of 10% until final completion
  Broad indemnity – multiple parties
GC